## action plan
action number | ACTIONS and ACTIVITIES | RESPONSIBLE | PARTICIPANTS | START | END | STATUS | NOTE | ott 19-mar 20 | apr 20- sett 20 | ott 20-mar 21 | apr 21- sett 21 | ott 21-mar 22 | apr 22- sett 22 | ott 22-mar 23 | apr 23- sett 23 | ott 23-nov 23
A1 | PROJECT ACTION PLAN | CORILA | all | 2019-10-01 | 2019-12-30 | concluded |  | MA1-DA1
A2 | EXECUTIVE PLANS | Provv.OO.PP | Provv.OO.PP, SELC | 2019-10-01 | 2019-11-30 | concluded
A2.1 | Executive plans of habitat and species management works and permits | SELC | SELC | 2019-10-01 | 2019-11-30 | concluded |  | DA2.1
A2.2 | Executive plan of the hydraulic works | Provv.OO.PP | Provv.OO.PP | 2019-10-01 | 2019-11-30 | concluded |  | DA2.2
A3 | APPROPRIATE ASSESSMENT (VINCA) | SELC | SELC | 2019-10-01 | 2020-02-28 | concluded |  | MA3.1 DA3 MA3.2
| Final report writing |  |  | 2019-10-01 | 2019-11-30 | concluded
| Final approval by competent authorities |  |  | 2019-12-01 | 2020-02-28 | concluded
A4 | SUBCONTRACTING AND GREEN PROCUREMENT PROCEDURES | CORILA | all | 2019-10-01 | 2019-11-30 | concluded |  | MA4.1 MA4.2 DA4.1 DA4.2
A5 | REVIEW AND ANALYSIS OF EXISTING ENVIRONMENTAL DATA ON THE INTERVENTION SITES | CORILA | all | 2019-10-01 | 2019-11-30 | concluded |  | DA5
A6 | HYDRO-GEOLOGICAL, WATER AND SOIL CHARACTERIZATION OF INTERVENTION SITES | SELC | SELC, Coop.Prim. | 2019-10-01 | 2020-10-30 | started |  | MA6.1 MA6.2 MA6.3 MA6.4 | MA6.5 | MA6.6 DA6
| Hydrogeology:piezometers positioning |  |  | 2019-10-01 | 2019-10-30 | concluded
| Hydrogeology:sampling of groundwater (monthly) |  |  | 2019-10-01 | 2020-10-30 | started
| Surface water: 1° quality monitoring |  |  | 2019-11-01 | 2019-11-30 | concluded
| Surface water: 2° quality monitoring |  |  | 2020-02-01 | 2020-02-28 | not started
| Surface water: 3° quality monitoring |  |  | 2020-05-01 | 2020-05-30 | not started
| Surface water: 4° quality monitoring |  |  | 2020-08-01 | 2020-08-30 | not started
| Soil surveys |  |  | 2019-11-01 | 2020-05-30 | started
| Bathymetric survey |  |  | 2019-10-01 | 2019-11-30 | concluded
A7 | VEGETATION AND HABITAT MAPS UPDATING | SELC | SELC | 2019-10-01 | 2020-09-30 | started |  | MA7.1 | MA7.2 | DA7
| Drone campaign and GPS measuring |  |  | 2019-10-01 | 2020-04-30 | started
| Updating of the available vegetation and habitat maps |  |  | 2019-11-01 | 2020-09-30 | started
| Phytosociological relevés for the updating of the available vegetation and habitat maps |  |  | 2019-10-01 | 2019-11-30 | concluded
| Phytosociological relevés: plot |  |  | 2020-05-01 | 2020-09-30 | not started
A8 | BIRDS MONITORING IN WINTER AND BREEDING SEASON | SELC | SELC | 2019-11-01 | 2020-08-30 | started |  | MA8.1 |  | MA8.2 DA8.1
| Fixed radius point counts:winter monitoring (fortnightly) |  |  | 2019-11-01 | 2020-02-28 | started
| Fixed radius point counts:summer monitoring (fortnightly) |  |  | 2020-05-01 | 2020-08-30 | not started
| Wintering birds monitoring (fortnightly) |  |  | 2019-12-01 | 2020-01-30 | not started
| Breeding birds monitoring (fortnightly) |  |  | 2020-05-01 | 2020-07-30 | not started
A9 | INVASIVE FISH SPECIES (Silurus glanis) DETECTION | WWF OASI | WWF OASI, Coop.Prim. | 2020-01-01 | 2020-01-30 | not started |  | MA9 | DA9
| Mapping channels |  |  | 2020-01-01 | 2020-01-30
| Silurus detection |  |  | 2020-01-01 | 2020-01-30
C1 | HYDRAULIC WORKS TO IMPROVE WATER CIRCULATION AND QUALITY | WWF OASI | WWF OASI, Coop.Prim., PROVV.OO.PP | 2019-10-01 | 2023-09-30 | started |  | MC1.1 MC1.2 | DC1.1 | MC1.3 | DC1.2 |  |  |  | MC1.4 | DC1.3
| Preliminary activities |  |  | 2019-10-01 | 2020-03-30 | started
| Dredging |  |  | 2020-02-01 | 2020-03-30 | not started
| Sluice gates laying |  |  | 2020-03-01 | 2020-04-30 | not started
| Fascines laying |  |  | 2020-03-01 | 2020-04-30 | not started
| Monitoring in continuos with sensors inside the piezometres |  |  | 2020-10-01 | 2023-09-30 | not started
| Monitoring in continuos with sensors in the channels |  |  | 2020-10-01 | 2023-09-30 | not started
C2 | PROTECTING AND INCREASING 7210*CLADIUM HABITAT | COOP PRIMAVERA | Coop.Prim.,WWF OASI,SELC | 2020-01-01 | 2022-03-30 | not started |  | MC2.1 | DC2.1 | MC2.2 MC2.3 | DC2.2 | MC2.4 | DC2.3
| Blackberry removal |  |  | 2020-01-01 | 2020-03-30
| Topsoil removal |  |  | 2020-03-01 | 2020-03-30
| 1° Planting |  |  | 2020-04-01 | 2020-05-30
| 2° Planting |  |  | 2021-03-01 | 2021-04-30
| 1°eventually dead plants replacing |  |  | 2021-02-01 | 2021-03-30
| 2° eventually dead plants replacing |  |  | 2022-02-01 | 2022-03-30
| 1°manual control of weeds |  |  | 2020-10-01 | 2020-11-30
| 2° manual control of weeds |  |  | 2021-10-01 | 2021-11-30
| 3° manual control of weeds |  |  | 2022-10-01 | 2022-11-30
C3 | RESTORING AND INCREASING 91E0* ALLUVIAL FOREST HABITAT | COOP PRIMAVERA | Coop.Prim.,WWF OASI,SELC | 2020-01-01 | 2022-04-30 | not started |  |  | MC3.1 | DC3.1 | MC3.2 | DC3.2 | MC3.3 | DC3.3
| 1° Topsoil removal |  |  | 2020-03-01 | 2020-04-30
| 2° Topsoil removal |  |  | 2020-12-01 | 2020-12-30
| 3° Topsoil removal |  |  | 2021-12-01 | 2021-12-30
| 1° Blackberry removal |  |  | 2020-02-01 | 2020-03-30
| 2° Blackberry removal |  |  | 2020-10-01 | 2020-11-30
| 3° Blackberry removal |  |  | 2021-10-01 | 2021-11-30
| 1° Planting |  |  | 2020-03-01 | 2020-04-30
| 2° Planting |  |  | 2020-12-01 | 2021-04-30
| 3° Planting |  |  | 2021-10-01 | 2022-02-28
| 1°manual control of weeds |  |  | 2021-03-01 | 2021-04-30
| 2° manual control of weeds |  |  | 2022-03-01 | 2022-04-30
| 3° manual control of weeds |  |  | 2023-03-01 | 2023-04-30
| Greenhouse construction |  |  | 2020-03-01 | 2020-03-30
| Construction of an external nursery |  |  | 2020-05-01 | 2020-06-30
| Harvesting seeds and planting in a greenhouse |  |  | 2020-03-01 | 2020-11-30
| Planting seedlings in the external nursery |  |  | 2020-06-01 | 2020-06-30
| 1°eventually dead plants replacing |  |  | 2021-02-01 | 2021-03-30
| 2° eventually dead plants replacing |  |  | 2022-02-01 | 2022-03-30
| 3°eventually dead plants replacing |  |  | 2023-02-01 | 2023-03-30
C4 | RAFT BUILDING FOR BREEDING WADERS AND TERNS | WWF OASI | WWF OASI, Coop.Prim., PROVV.OO.PP | 2020-01-01 | 2023-09-30 | not started |  |  | MC4.1 DC4.1 | [5 empty] | MC4.2 | DC4.2
| Rafts building |  |  | 2020-02-01 | 2020-03-30
| Rafts placing 1°year |  |  | 2020-04-01 | 2020-04-30
| Rafts landing 1°year |  |  | 2020-08-01 | 2020-08-30
| Rafts maintenance 1°year |  |  | 2020-09-01 | 2021-03-30
| Rafts placing 2° year |  |  | 2021-04-01 | 2021-04-30
| Rafts landing 2° year |  |  | 2021-08-01 | 2021-08-30
| Rafts maintenance 2° year |  |  | 2021-09-01 | 2022-03-30
| Rafts placing 3° year |  |  | 2022-04-01 | 2022-04-30
| Rafts landing 3° year |  |  | 2022-08-01 | 2022-08-30
| Rafts maintenance 3° year |  |  | 2022-09-01 | 2023-03-30
| Rafts placing 4° year |  |  | 2023-04-01 | 2023-04-30
| Rafts landing 4° year |  |  | 2023-08-01 | 2023-08-30
| Rafts maintenance 4° year |  |  | 2023-09-01 | 2023-09-30
C5 | REDUCTION OF PLANT INVASIVE SPECIES OCCURRENCE | COOP PRIMAVERA | Coop.Prim.,SELC | 2020-02-01 | 2022-11-30 | not started |  |  | MC5.2 DC5.1 | MC5.1 MC5.3 | MC5.4 DC5.2 | MC5.5 | MC5.6 DC5.3 | MC5.7
| B.halimifolia:eradication |  |  | 2020-02-01 | 2020-09-30
| R.Pseudoacacia:cleaning surfaces |  |  | 2020-10-01 | 2020-11-30
| R.Pseudoacacia:adults cutting |  |  | 2020-10-01 | 2020-11-30
| R.Pseudoacacia:1°planting of native species |  |  | 2020-10-01 | 2020-11-30
| R.Pseudoacacia:1° cutting of eventual coppice shoot,scutting of the individuals of minor size |  |  | 2021-10-01 | 2021-11-30
| R.Pseudoacacia:2° planting of native species |  |  | 2021-10-01 | 2021-11-30
| R.Pseudoacacia:2° cutting of re-shooted coppices |  |  | 2022-06-01 | 2022-06-30
| R.Pseudoacacia:3° cutting of re-shooted coppices |  |  | 2022-10-01 | 2022-10-30
| R.Pseudoacacia:1°eventually dead plants replacing |  |  | 2021-02-01 | 2021-03-30
| R.Pseudoacacia:2°eventually dead plants replacing |  |  | 2022-02-01 | 2022-03-30
| R.Pseudoacacia:3°eventually dead plants replacing |  |  | 2023-03-01 | 2023-03-30
| R.Pseudoacacia:1°manual control of weeds |  |  | 2021-03-01 | 2021-04-30
| R.Pseudoacacia:2°manual control of weeds |  |  | 2022-03-01 | 2022-04-30
| R.Pseudoacacia:3°manual control of weeds |  |  | 2023-03-01 | 2023-03-30
C6 | INVASIVE FISH SPECIES (Silurus glanis) CONTROL | WWF OASI | WWF OASI, Coop.Prim. | 2020-01-01 | 2023-03-30 | not started |  | MC6.1 | DC6.1 | MC6.2 | DC6.2 | MC6.3 | DC6.3 | MC6.4 |  | DC6.4
| 1°year capture |  |  | 2020-01-01 | 2020-03-30
| 2° year capture |  |  | 2021-01-01 | 2021-03-30
| 3° year capture |  |  | 2022-01-01 | 2022-03-30
| 4° year capture |  |  | 2023-01-01 | 2023-03-30
C7 | VISITOR EXPERIENCE ENHANCEMENT | WWF OASI | WWF OASI, Coop.Prim. | 2020-03-01 | 2020-05-30 | not started |  |  | DC7
D1 | HYDROLOGICAL AND MORPHOLOGICAL MONITORING | SELC | SELC,Coop.Prim. | 2020-11-01 | 2023-07-30 | not started |  |  |  | MD1.1 | MD1.2 DD1.1 |  | MD 1.3 DD1.2 |  | MD1.4 DD1.3
| 1° water surface samples |  |  | 2020-11-01 | 2020-11-30
| 2° water surface samples |  |  | 2021-03-01 | 2021-03-30
| 3° water surface samples |  |  | 2021-07-01 | 2021-07-30
| 4° water surface samples |  |  | 2021-11-01 | 2021-11-30
| 5° water surface samples |  |  | 2022-03-01 | 2022-03-30
| 6° water surface samples |  |  | 2022-07-01 | 2022-07-30
| 7° water surface samples |  |  | 2022-11-01 | 2022-11-30
| 8° water surface samples |  |  | 2023-03-01 | 2023-03-30
| 9° water surface samples |  |  | 2023-07-01 | 2023-07-30
| 1° fascines monitoring |  |  | 2021-05-01 | 2021-05-30
| 2° fascines monitoring |  |  | 2022-05-01 | 2022-05-30
| 3° fascines monitoring |  |  | 2023-05-01 | 2023-05-30
D2 | VEGETATION MONITORING | SELC | SELC | 2020-05-01 | 2023-09-30 | not started |  |  | MD2.1 |  | DD2.1 |  | DD2.2 |  | MD2.2 DD2.3
| 1°morphometric surveys action C2 |  |  | 2022-05-01 | 2022-05-30
| 2° morphometric surveys action C2 |  |  | 2023-05-01 | 2023-05-30
| 1°plot surveys action C2 |  |  | 2020-05-01 | 2020-07-30
| 2° plot surveys action C2 |  |  | 2021-05-01 | 2021-07-30
| 3° plot surveys action C2 |  |  | 2022-05-01 | 2022-07-30
| 4° plot surveys action C2 |  |  | 2023-05-01 | 2023-07-30
| 1°dendrometric surveys action C3 |  |  | 2021-05-01 | 2021-05-30
| 2° dendrometric surveys action C3 |  |  | 2022-05-01 | 2022-05-30
| 1°plot surveys action C3 |  |  | 2020-06-01 | 2020-07-30
| 2° plot surveys action C3 |  |  | 2021-05-01 | 2021-07-30
| 3° plot surveys action C3 |  |  | 2022-05-01 | 2022-07-30
| 4° plot surveys action C3 |  |  | 2023-05-01 | 2023-07-30
| 1° monitoring action C5 |  |  | 2021-04-01 | 2021-06-30
| 2° monitoring action C5 |  |  | 2023-04-01 | 2023-06-30
| 1° soil samples |  |  | 2020-04-01 | 2020-04-30
| 2° soil samples |  |  | 2020-09-01 | 2020-09-30
| 3° soil samples |  |  | 2021-04-01 | 2021-04-30
| 4° soil samples |  |  | 2021-09-01 | 2021-09-30
| 5° soil samples |  |  | 2022-04-01 | 2022-04-30
| 6° soil samples |  |  | 2022-09-01 | 2022-09-30
| 7° soil samples |  |  | 2023-04-01 | 2023-04-30
| 8° soil samples |  |  | 2023-09-01 | 2023-09-30
| Drone campaign |  |  | 2023-04-01 | 2023-04-30
D3 | EFFECTS OF PROJECT ACTONS ON WINTERING AND BREEDING BIRDS | SELC | SELC | 2020-05-01 | 2023-08-30 | not started |  |  |  | MD3.1 | DD3.1 |  | DD3.2 |  | MD3.2 DD3.3
| fixed radius point counts: 1°winter monitoring (fortnightly) |  |  | 2020-11-01 | 2021-02-28
| fixed radius point counts: 1°summer monitoring (fortnightly) |  |  | 2021-05-01 | 2021-08-30
| fixed radius point counts:2°winter monitoring (fortnightly) |  |  | 2021-11-01 | 2022-02-28
| fixed radius point counts:2°summer monitoring (fortnightly) |  |  | 2022-05-01 | 2022-08-30
| fixed radius point counts:3°winter monitoring (fortnightly) |  |  | 2022-11-01 | 2023-02-28
| fixed radius point counts:3°summer monitoring (fortnightly) |  |  | 2023-05-01 | 2023-08-30
| 1°wintering birds monitoring (fortnightly) |  |  | 2020-12-01 | 2021-01-30
| 2° wintering birds monitoring (fortnightly) |  |  | 2021-12-01 | 2022-01-30
| 3° wintering birds monitoring (fortnightly) |  |  | 2022-12-01 | 2023-01-30
| 1°breeding birds monitoring (fortnightly) |  |  | 2021-05-01 | 2021-06-30
| 2° breeding birds monitoring (fortnightly) |  |  | 2022-05-01 | 2022-06-30
| 3° breeding birds monitoring (fortnightly) |  |  | 2023-05-01 | 2023-06-30
D4 | INVASIVE FISH SPECIES (Silurus glanis) OCCURRENCE | WWF OASI | WWF OASI | 2020-01-01 | 2023-03-30 | not started |  | MD4.1 | DD4.1 | MD4.2 | DD4.2 | MD4.3 | DD4.3 | MD4.4 | DD4.4
| 1°year Silurus monitoring |  |  | 2020-01-01 | 2020-03-30
| 2° year Silurus monitoring |  |  | 2021-01-01 | 2021-03-30
| 3° year Silurus monitoring |  |  | 2022-01-01 | 2022-03-30
| 4° year Silurus monitoring |  |  | 2023-01-01 | 2023-03-30
D5 | SOCIO ECONOMIC IMPACT | CORILA | CORILA | 2019-10-01 | 2023-09-30 | started |  | DD5.1 | [6 empty] | MD5.1 MD5.2 | DD5.2
D6 | PROJECT IMPACTS ON THE ECOSYSTEM FUNCTIONS | CORILA | CORILA | 2020-04-01 | 2023-09-30 | not started
D6.1 | Ex-ante ecosystem services assessment | CORILA | CORILA | 2020-04-01 | 2020-09-30 |  |  |  |  | DD6.1 | [5 empty] | MD6.2
D6.2 | Ex-post ecosystem services assessment and evaluation of the project’s impact on ecosystem services | CORILA | CORILA | 2023-04-01 | 2023-09-30 | [10 empty] | DD6.2
D7 | PROJECT PERFORMANCE INDICATORS MONITORING | CORILA | ALL | 2020-08-01 | 2023-09-30 | not started
| 1°indicators monitoring (mid term report) |  |  | 2021-02-01 | 2021-09-30 |  |  |  |  | MD7.1 DD7.1
| 2° indicators monitoring (final report) |  |  | 2023-08-01 | 2023-08-30 | [9 empty] | MD7.2 | DD7.2
E1 | DISSEMINATION PLANNING AND EXECUTION | CORILA | ALL | 2019-10-01 | 2023-09-30 | started
E1.1 | Dissemination and communication plan | CORILA | ALL | 2019-10-01 | 2019-12-30 | started |  | DE1.1
E1.2 | Networking with other projects (LIFE and/or NON LIFE projects) | CORILA | ALL | 2019-10-01 | 2023-09-30 | started
E1.3 | Development of the dissemination pack (website, brochures, Layman's Report, notice boards ) | CORILA | ALL | 2019-10-01 | 2023-09-30 | started |  | DE1.3.1 DE.1.3.2 DE.1.3.3 | [6 empty] | DE.1.3.4 | DE.1.3.5 DE.1.3.6
E1.4 | Environmental education and awareness on Natura 2000 network | CORILA | ALL | 2020-03-01 | 2023-05-30 | not started |  | DE.1.4.1 |  | ME1.4.1 |  | ME1.4.2 DE.1.4.2 |  | ME1.4.3 |  | ME1.4.4 DE.1.4.3
| spring open days 1°year |  |  | 2020-03-01 | 2020-05-30
| spring open days 2° year |  |  | 2021-03-01 | 2021-05-30
| spring open days 3°year |  |  | 2022-03-01 | 2022-05-30
| spring open days 4° year |  |  | 2023-03-01 | 2023-05-30
| autumn open days 1°year |  |  | 2020-09-01 | 2020-11-30
| autumn open days 2° year |  |  | 2021-09-01 | 2021-11-30
| autumn open days 3°year |  |  | 2022-09-01 | 2022-11-30
| autumn open days 4° year |  |  | 2023-09-01 | 2023-09-30
| school days 1°year |  |  | 2020-04-01 | 2020-05-30
| school days 2° year |  |  | 2021-04-01 | 2021-05-30
| school days 3°year |  |  | 2022-04-01 | 2022-05-30
| school days 4° year |  |  | 2023-04-01 | 2023-05-30
E1.5 | Effective dissemination to the general public (Broadcast media, WMK Plan, Personal contacts) | CORILA | ALL | 2019-10-01 | 2023-09-30 | started |  |  |  | ME1.5.1 |  | ME1.5.2 |  | ME1.5.3 |  | ME1.5.4
E2 | ACTIVITIES TO ENSURE REPLICABILITY OR TRANSFERABILITY | CORILA | ALL | 2019-10-01 | 2023-09-30 | not started
E2.1 | Dissemination activities targeted to local eco-tourism-stakeholders group | CORILA | ALL | 2019-10-01 | 2023-09-30 |  |  |  |  | ME2.1.1 DE2.1.1 |  |  |  | ME2.1.2 DE2.1.2
E2.2 | Strategic Transferability Plan for Conservation Management and Habitat Restoration for Wetlands | CORILA | ALL | 2019-10-01 | 2023-09-30 |  |  |  | DE2.2.1 |  | ME2.2.1 | DE2.2.2 | DE2.2.3 | DE2.2.4 | ME2.2.2 DE2.2.5
F1 | PROJECT MANAGEMENT BY CORILA | CORILA | ALL | 2019-10-01 | 2023-09-30 | started |  |  |  | MF1 DF1.1 | [5 empty] | DF1.2
F2 | PROJECT MONITORING ACTIVITIES | CORILA | ALL | 2019-10-01 | 2023-09-30 | started |  |  |  | MF2.1 DF2.1 |  | MF2.2 DF2.2 |  | MF2.3 DF2.3 | DF2.4 MF2.4
F3 | PROJECT MEETINGS AND CONFERENCES | CORILA | ALL | 2019-10-01 | 2023-09-30 | started |  | MF3.1 DF3.1 |  | MF3.2 DF3.2 |  | MF3.3 DF3.3 DF3.4 |  | MF3.4 DF3.5 | MF3.5 DF3.6 DF3.7
| 1°steering commitee |  |  | 2020-10-01 | 2020-10-30 | not started
| 2° steering commitee |  |  | 2021-10-01 | 2021-10-30 | not started
| 3° steering commitee |  |  | 2022-10-01 | 2022-10-30 | not started
| 4° steering commitee |  |  | 2023-06-01 | 2023-06-30 | not started
| Kick Off Meeting |  |  | 2019-12-01 | 30/12/219 | concluded
| Mid term conference |  |  | 2021-10-01 | 2021-10-30 | not started
| Final conference |  |  | 2023-06-01 | 2023-06-30 | not started
F4 | AFTER LIFE PLAN | CORILA | ALL | 2023-09-01 | 2023-09-30 | started | [8 empty] | MF4 | DF4

## STATUS
STATUS actions
not started
started
concluded
status deliverable and milestones
CONCLUDED
SUBMITTED
status purchases end external
PROCEDURE NOT STARTED
PROCEDURE IN PROGRESS
CONCLUDED