## settimanale
GANTT DIAGRAM - ACTION C2-C5
PROCESSING BY ACTION | YEAR
|  | 2019 |  |  | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023
| MONTHS | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September
C2
Eliminazione della vegetazione infestante
Scotico superficiale del terreno
Impianto di specie tipiche dell'habitat 7210*
Sostituzione fallanze
Controllo manuale infestanti
C3
Eliminazione della vegetazione infestante
Scotico superficiale del terreno
Realizzazione serra
Realizzazione vivaio esterno
Raccolta semi e piantumazione in serra
Piantumazione piantine nel vivaio esterno
Impianto di specie tipiche dell'habitat 91E0*
Sostituzione fallanze
Controllo manuale infestanti
C4
Costruzione zattere
Posa zattere
Rimozione zattere
Manutenzione zattere e stoccaggio
C5
B. halimifolia: eradicazione
R. pseudoacacia: pulizia superficie
R. pseudoacacia: taglio adulti
R. pseudoacacia: impianto specie tipiche
R. pseudoacacia: taglio ricacci e giovani
R. pseudoacacia: sostituzione fallanze specie tipiche
R. pseudoacacia: controllo manuale infestanti
C6